## 01_Project_Overview
Table 1: Project Overview
Field | Data
Project Name | CV Catalog & Portfolio Hub
Architecture | Serverless Static Web Application
Methodology | Agile (Kanban) with Shift-Left/Shift-Right DevOps Practices
Overview | A high-performance, static portfolio catalog hosted on Firebase and routed via Cloudflare. Designed to showcase student CVs and Godot WASM games. To maintain a $0 budget and guarantee stability, the project utilizes manual data integration, HTML data-attribute filtering, and automated CI/CD pipelines.
Problem Definition | Students' resumes and portfolio contents are disorganized ,Increased deployment and maintenance risks, resulting in wasted time

## 02_Team_Roles
Table 2: Team Members & Roles
Member Name | Role | Responsibilities
Berkant | Lead DevOps & Full Stack | Manages cloud infrastructure (Firebase Hosting), DNS routing via Cloudflare, GitHub repository management, CI/CD pipelines, and core static site architecture.
Ümit | Project Manager & UI Lead | Manages Jira task tracking, develops the frontend UI and vanilla JavaScript filtering systems, and handles manual integration of student assets.

## 03_Timeline
Table 3: Timeline & Schedule Management
Week | Dates | Phase | Planned Activities
Week 1 | Mar 01 - Mar 07 | Architecture & Setup | Jira setup, Firebase initialization, GitHub repo creation, and CI/CD Action pipelines configured.
Week 2 | Mar 08 - Mar 14 | UI & Logic Implementation | Develop static HTML/Tailwind structure, build JavaScript filtering logic, and establish Google Forms ingestion pipeline.
Week 3 | Mar 15 - Mar 21 | Asset Integration | Manual entry of student CVs, lazy-loading implementation for WASM games, and image compression.
Week 4 | Mar 22 - Mar 30 | QA & Deployment | Final cross-browser testing, merge to main branch, production deployment, and monitoring Cloudflare analytics.

## 04_Budget
Table 4: Budget Planning
Resource Type | Allocation | Notes
Time | 4 Weeks | March 1, 2026 - March 30, 2026
Members | 2 Students | Cross-functional responsibilities
Financial Cost | $0.00 | Utilizing exclusively free-tier enterprise tools.
Infrastructure | Firebase (Spark), Cloudflare (Free), GitHub | Handles hosting, DNS, and version control at zero cost.

## 05_Risk_Management
Table 5: Risk Management
Identified Risk | Impact | Mitigation Strategy
CI/CD Deployment failures (Docker/Aspire) | High | Pivoted to static Firebase hosting to guarantee successful delivery within strict time limits.
Bandwidth limits exceeded by large WASM games | Medium | Implement lazy-loading for all Godot games; games only load when users explicitly click 'Play'.