## Risk Identification
Risk | Description
Data Security Risk | Possible leakage of users' personal information
AI Filtering Errors | AI may incorrectly filter suitable candidates
System Performance Issues | Platform may slow down with many users
Fake CV Uploads | Users may upload incorrect or misleading CV information
Multi-language Errors | Translation or language system failures
AI Resource Contention | Background AI worker might starve the main Flask process of CPU/RAM

## Risk Evaluation
Risk | Probability | Impact | Risk Level
Data Security | Medium | Very High | High
AI Filtering Errors | Medium | High | High
System Performance | Medium | Medium | Medium
Fake CV | High | Medium | High
Language Errors | Low | Medium | Low

## Risk Mitigation
Risk | Preventive Action
Data Security | Encrypt stored data and secure database access
AI Filtering Errors | Regularly test and retrain AI model
System Performance | Use server optimization and caching
Fake CV | Add user verification system
Language Errors | Use reliable translation APIs

## Risk Matrix
Impact / Probability | Low | Medium | High
High Impact |  | AI Filtering | Data Security
Medium Impact | Language Errors | Performance Issues | Fake CV
Low Impact

## Security & Privacy
Security Measures
User authentication system
HTTPS secure communication
Protection against SQL Injection and XSS
Encrypted data storage
Controlled access to CV data
Cloudflare Turnstile Integration
SQLite WAL Mode for Concurrency Protection

## Application Roadmap
Stage | Description
Research | Study CV platforms and AI filtering systems
System Design | Design database, user roles and architecture
Backend Development | Develop user management and database operations
Frontend Development | Create user interface
AI Filtering System | Develop AI-based CV filtering
Testing | Run system tests and bug fixes
Deployment | Publish the platform
AI Background Worker | Native background process for model inference
i18n System | JSON-based translation engine (EN/TR)

## Validation & Testing Plan
Test Phase | Test Type | Description / Method | Tools to be Used | Success Criteria / Acceptance Criteria
Unit Testing | Module-Based Testing | Check that each function (CV upload, user login, AI filtering call, etc.) works correctly independently. | JUnit (Java), Jest (JS), PyTest | All unit tests must pass with a 90% success rate; no critical errors.
Integration Testing | API & Database Testing | Verify that communication between frontend and backend, database queries, and AI service integration work smoothly. | Postman, Supertest, REST Assured | All API requests must return successful responses; data consistency must be ensured
Functional Testing | User Scenarios | Simulate real user behavior to test core functions: CV upload, CV viewing, AI filtering, language switching. | Selenium, Cypress, manual testing | All scenarios must be completed without errors; user flows should work seamlessly.
Performance Testing | Load & Stress Testing | Measure system resilience under concurrent users and data volume. Target: Response time < 2 seconds with 1000 concurrent users. | JMeter, Locust, k6 | Average response time < 2 seconds; error rate < 1%.
Security Testing | Vulnerability Scan | Detect security vulnerabilities such as SQL Injection, XSS, unauthorized access. | OWASP ZAP, Burp Suite | No critical or high-risk vulnerabilities; all security measures must be actively working.
User Acceptance Test | Beta User Testing | Evaluate system usability and functionality with real users (students, employers) | Surveys, observation, feedback | At least 80% of users report satisfaction; no critical errors reported.
Validation Method | Code Review | Check code quality and compliance with standards through team-based code reviews. | GitHub pull requests, checklists | All code must be reviewed and approved by at least one team member.

## Success Criteria
Criteria
Students can upload their CVs
Employers can view candidate CVs
AI can filter candidates effectively
Platform supports multiple languages
User data remains secure
System works fast and reliably
AI-powered candidate summary generation
Seamless Godot WebGL execution with Cross-Origin Isolation