## 01_Project_Overview
Table 1: Project Overview
Field | Data
Project Name | CV Catalog & Portfolio Hub
Architecture | Flask + SQLite + HTMX + Local AI
Methodology | Agile (Kanban) with Shift-Left/Shift-Right DevOps Practices
Overview | A high-performance unified platform serving Godot WebGL portfolios and native interactive CV talent pools. Built with Flask, SQLite (WAL mode), and HTMX for maximum efficiency on constrained hardware (8GB RAM). Features a local Qwen 2.5 7B AI model for translations and candidate analysis.
Problem Definition | Traditional platforms are resource-heavy and slow. Developers need a low-latency, unified hub to showcase WASM games and interactive resumes without enterprise overhead.

## 02_Team_Roles
Table 2: Team Members & Roles
Member Name | Role | Responsibilities
Berkant | Lead DevOps & Full Stack | Manages cloud infrastructure (Firebase Hosting), DNS routing via Cloudflare, GitHub repository management, CI/CD pipelines, and core static site architecture.
Berkant | Lead Software Architect & DevOps | Develops core Flask architecture, SQLite DAL, HTMX interactions, and AI background worker systems. Manages local server deployment and CI/CD.
Ümit | Project Manager & Frontend Specialist | Oversees UI/UX design using Pico.css and custom theme variables. Manages Jira tasks and ensures premium aesthetics and mobile responsiveness.

## 03_Timeline
Table 3: Timeline & Schedule Management
Week | Dates | Phase | Planned Activities
Week 1 | Mar 01 - Mar 07 | Architecture & Setup | Jira setup, Firebase initialization, GitHub repo creation, and CI/CD Action pipelines configured.
Week 2 | Mar 01 - Mar 14 | UI & Logic Implementation | Develop static HTML/Tailwind structure, build JavaScript filtering logic, and establish Google Forms ingestion pipeline.
Week 3 | Mar 15 - Mar 31 | Asset Integration | Manual entry of student CVs, lazy-loading implementation for WASM games, and image compression.
Week 4 | Apr 01 - Apr 15 | AI Integration & i18n | Implementing Local Qwen model, background workers, and English/Turkish translation system.
| Apr 16 - Apr 30 | Refactoring & Selective Porting | Consolidating features from experimental branches into the stable dev branch. Final QA and performance tuning.

## 04_Budget
Table 4: Budget Planning
Resource Type | Allocation | Notes
Time | 4 Weeks | March 1, 2026 - March 30, 2026
Members | 8 Weeks | Cross-functional responsibilities
Financial Cost | 2 Students | Utilizing exclusively free-tier enterprise tools.
Infrastructure | Firebase (Spark), Cloudflare (Free), GitHub | Handles hosting, DNS, and version control at zero cost.
Local Server (8GB RAM), SQLite, HTMX, Pico.css, Qwen 2.5 7B

## 05_Risk_Management
Table 5: Risk Management
Identified Risk | Impact | Mitigation Strategy
CI/CD Deployment failures (Docker/Aspire) | High | Pivoted to static Firebase hosting to guarantee successful delivery within strict time limits.
Bandwidth limits exceeded by large WASM games | Medium | Optimized SQLite with WAL mode and request-scoped connections. Implemented background task queue for heavy AI ops.
Local AI Model Memory Usage | Very High | Utilized 4-bit quantization and lazy-loading for AI models to fit within 8GB RAM budget.